## Sheet1
PI_ID | PI | Sprint | App | Feature_ID | Feature | Story_ID | User Story | Story Points | Task_ID | Task | Description | Assignee | Start Date | End Date | Status | Capacity | Sprint Start Date | Sprint End Date | Spill over | Backlog
PI1 | PI Planning -2 | Sprint 1 | The CliniQ Mobile App | F1 | UI/UX | S1 | Home UI - Bannner | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-01 | 2026-04-10
PI1 | PI Planning -2 | Sprint 1 | The CliniQ Mobile App | F1 | UI/UX | S1 | Home UI - Expert Doctors | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-01 | 2026-04-10
PI1 | PI Planning -2 | Sprint 1 | The CliniQ Mobile App | F1 | UI/UX | S1 | Home UI - All Doctor | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-01 | 2026-04-10
PI1 | PI Planning -2 | Sprint 1 | The CliniQ Mobile App | F1 | UI/UX | S1 | Home UI - Different Doctor Categories | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-01 | 2026-04-10
PI1 | PI Planning -2 | Sprint 1 | The CliniQ Mobile App | F1 | UI/UX | S1 | Home UI - Reviews and Testimonials | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-01 | 2026-04-10
PI1 | PI Planning -2 | Sprint 1 | The CliniQ Mobile App | F1 | UI/UX | S2 | Appointment UI - Doctor Card | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-01 | 2026-04-10
PI1 | PI Planning -2 | Sprint 1 | The CliniQ Mobile App | F1 | UI/UX | S2 | Appointment UI - Slot Design | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-01 | 2026-04-10
PI1 | PI Planning -2 | Sprint 1 | The CliniQ Mobile App | F1 | UI/UX | S2 | Appointment UI - Different Colors for Home and Teleconsultation | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-01 | 2026-04-10
PI1 | PI Planning -2 | Sprint 1 | The CliniQ Mobile App | F1 | UI/UX | S3 | My Appointments UI - Card redesign | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-01 | 2026-04-10
PI1 | PI Planning -2 | Sprint 1 | The CliniQ Mobile App | F1 | UI/UX | S3 | My Appointments UI - Different Colors for Home and Teleconsultation | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-01 | 2026-04-10
PI1 | PI Planning -2 | Sprint 1 | The CliniQ Mobile App | F1 | UI/UX | S3 | My Appointments UI - UI Improvement | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-01 | 2026-04-10
PI1 | PI Planning -2 | Sprint 1 | The CliniQ Mobile App | F1 | UI/UX | S4 | Profile UI - Redesign | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-01 | 2026-04-10
PI1 | PI Planning -2 | Sprint 1 | The CliniQ Mobile App | F1 | UI/UX | S5 | Prescription page UI - Redesign card | 2 |  |  |  | Kalyan |  |  | Inprogress | 10 | 2026-04-01 | 2026-04-10
PI1 | PI Planning -2 | Sprint 2 | Admin Web App | F2 | Web App | S6 | admin - webapp conversion | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Admin Web App | F2 | Web App | S7 | Letter maker | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Admin Web App | F2 | Web App | S8 | Letter number Fix | 2 |  |  |  | Kalyan |  |  | Defined | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Admin Web App | F2 | Web App | S9 | Annexures | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Admin Web App | F2 | Web App | S10 | Search Bar | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Admin Web App | F2 | Web App | S11 | Chat Viewer | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Admin Web App | F2 | Web App | S12 | Onbarding Stram Line | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Admin Web App | F2 | Web App | S13 | Payslip generator | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Admin Web App | F2 | Web App | S14 | UI Enhancement | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Doctor Web App | F3 | Web App | S15 | doctor - webapp conversion | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Doctor Web App | F3 | Web App | S16 | Revenue Logic | 2 |  |  |  | Kalyan |  |  | Defined | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Doctor Web App | F3 | Web App | S17 | Prescription generation | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Doctor Web App | F3 | Web App | S18 | Medicine and Test List | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Doctor Web App | F3 | Web App | S19 | Auto suggestion on medicine and test | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Doctor Web App | F3 | Web App | S20 | UI enhancement | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Doctor Web App | F3 | Web App | S21 | Patient Directoty | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Doctor Web App | F3 | Web App | S22 | Signature in Prescription | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Doctor Web App | F3 | Web App | S23 | Appointment UI | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 2 | Doctor Web App | F3 | Web App | S24 | Appointment Logic | 2 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-11 | 2026-04-20
PI1 | PI Planning -2 | Sprint 3 | The CliniQ Mobile App | F4 | Logic | S25 | Appointment Logic - Booking Logic | 1 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-21 | 2026-04-30
PI1 | PI Planning -2 | Sprint 3 | The CliniQ Mobile App | F5 | Login | S26 | OTP Implementation | 3 |  |  |  | Kalyan |  |  | Inprogress | 10 | 2026-04-21 | 2026-04-30
PI1 | PI Planning -2 | Sprint 3 | The CliniQ Mobile App | F6 | Login | S27 | DLT regeistration | 3 |  |  |  | Kalyan |  |  | Defined | 10 | 2026-04-21 | 2026-04-30
PI1 | PI Planning -2 | Sprint 3 | The CliniQ Web App | F7 | Web App | S28 | Converting Mobile APP to web App | 1 |  |  |  | Kalyan |  |  | Completed | 10 | 2026-04-21 | 2026-04-30
PI1 | PI Planning -2 | Sprint 3 | The CliniQ Mobile App | F8 | Marketing | S29 | Meta Business Explore | 3 |  |  |  | Kalyan |  |  | Inprogress | 10 | 2026-04-21 | 2026-04-30
PI1 | PI Planning -2 | Sprint 3 | The CliniQ Mobile App | F9 | Marketing | S30 | Instagram Follower Activity | 5 |  |  |  | Kalyan |  |  | Defined | 10 | 2026-04-21 | 2026-04-30
PI1 | PI Planning -2 | Sprint 3 | The CliniQ Mobile App | F9 | Marketing | S31 | Facebook Follower Activity | 5 |  |  |  | Kalyan |  |  | Defined | 10 | 2026-04-21 | 2026-04-30
PI1 | PI Planning -2 | Sprint 3 | The CliniQ Mobile App | F9 | Marketing | S32 | Ad Ideas - Analysis | 5 |  |  |  | Sradha |  |  | Inprogress | 10 | 2026-04-21 | 2026-04-30
PI1 | PI Planning -2 | Sprint 3 | The CliniQ Mobile App | F9 | Marketing | S33 | Instagram post | 5 |  |  |  | Ruchi |  |  | Defined | 10 | 2026-04-21 | 2026-04-30
PI1 | PI Planning -2 | Sprint 3 | The CliniQ Mobile App | F9 | Marketing | S34 | Marketing Budget | 5 |  |  |  | Kalyan |  |  | Defined | 10 | 2026-04-21 | 2026-04-30
PI1 | PI Planning -2 | Sprint 3 | The CliniQ Mobile App | F9 | Doctor on boarding | S35 | Naukri or Linked in Profile | 2 |  |  |  | Kalyan |  |  | Defined | 10 | 2026-04-21 | 2026-04-30
PI1 | PI Planning -2 | Sprint 3 | The CliniQ Mobile App | F10 | Doctor on boarding | S36 | Other connections | 5 |  |  |  | Sradha |  |  | Defined | 10 | 2026-04-21 | 2026-04-30
PI1 | PI Planning -2 | Sprint 4 | The CliniQ Mobile App | F11 | Doctor on boarding | S37 | Other connections | 5 |  |  |  | Bapa |  |  | Defined | 10 | 2026-05-01 | 2026-05-10
PI2 | PI Planning -2 | Sprint 3 | The CliniQ Mobile App | F12 | UI/UX | S38 | The CliniQ - History and Appointment Cared Redesign | 2 |  |  |  | Kalyan |  |  | Defined | 10 | 2026-04-21 | 2026-04-30
PI2 | PI Planning -2 | Sprint 3 | The CliniQ Web App | F13 | UI/UX | S39 | Screen Flickring - Login screen | 2 |  |  |  | Kalyan |  |  | Defined | 10 | 2026-04-21 | 2026-04-30
PI2 | PI Planning -2 | Sprint 3 | The CliniQ Web App | F14 | UI/UX | S40 | Booking UI design | 2 |  |  |  | Kalyan |  |  | Defined | 10 | 2026-04-21 | 2026-04-30
PI2 | PI Planning -2 | Sprint 3 | The CLiniQ (Web + Mobile) | F15 | Logic | S41 | Traffic log (Web/Mobile) | 2 |  |  |  | Kalyan |  |  | Defined | 10 | 2026-04-21 | 2026-04-30
PI2 | PI Planning -2 | Sprint 3 | Doctor Mobile App | F16 | UI/UX | S42 | Prescription Functionality as Web App | 2 |  |  | Auto Suggestion of medicine and Test List, Medicine Time and Frequency | Kalyan |  |  | Defined | 10 | 2026-04-21 | 2026-04-30